## Summer2014
DMTF	DM		Activity Name	Length	assignee					days per assignee					total	Notes/description
				[days]	Jacek	Daniel	K-T	Serge	Bill	AndyH	AndyS	Fabrice	Jacek	Daniel	K-T	Serge	Bill	AndyH	AndyS	Fabrice	FTE-days
	DM-48	hack	Qserv: hackathon II (spring 2014)	7	100%	71%	65%	90%	71%	60%	71%	100%	7	5	5	6	5	4	5	7	44	including prep
	DM-51	config	Qserv configuration	20	25%					70%	100%	5					14	20	39	Design. Zookeeper-based configuration and starting of all qserv components, new node bootstrapping. Multiple small iterations
	DM-69	reorg	Tightening interfaces between Qserv core modules	15		100%			75%					15			11				26
DMTF-16570-09	DM-70	reorg	Rewriting XrootD-facing code	15		70%			50%	40%				11			8	6			24	rethink czar dispatch and worker scheduling framework
	DM-71	dd	Qserv design: data distribution	15	30%		5%			70%	50%		5		1			11	8		23	Design. Covers issues such as how new data (ingest and user generated) is added, fault recovery
	DM-56	css	Qserv Central State System – V2	15	100%			20%					15			3					18	improvements to the basic proof-of-concent prototype built during W14. E.g., watchers need work
	DM-209		Qserv: tools for cluster coordination (evaluation)	12		5%	5%	5%			20%	100%		1	1	1			2	12	16	evaluate cluster config tools such as Chef and Puppet, light prototyping
	DM-67	reorg	Collection of random refactoring for Qserv core (umbrella for smaller activities, these activities are captured separately)
DMTF-1640-20	DM-198	reorg	Integrating Ref*Match into qserv	8		60%		100%					5		8					13
	DM-210		Data ingest	10	15%			100%					2			10					12	Revisit/improve data ingest design, toy prototype zookeeper based prototype
	DM-211	reorg	Qserv: front-end rearchitect	10		100%	10%					10	1					11	proxy, down to xrootd client (mysqld, python, zookeeper). This about how to improve the architecture
DMTF-1650-045	DM-199	reorg	Develop new master-worker result system	10		100%		5%					10		1					11
	DM-195	reorg	Logging -v2	10					100%					10				10
	DM-205	reorg	Logging: migrate Qserv code to the new logging system	10					100%					10				10
	DM-215	reorg	C++ geometry primitives for Qserv	10		10%		90%					1		9					10
DMTF-16570-18	DM-200	testing	Qserv: automated testbed	5	10%					40%	100%	1					2	5	8
	DM-212	reorg	Migrate away from env variables	5		40%			100%					2			5				7	mostly just mechanics. Some design needed: config class, backend zookeeper based (maybe)
	DM-213	testing	Test Qserv with Winter 2014 data set	5	10%	10%		10%				100%	1	1		1				5	7
	DM-216	reorg	Switch Qserv to C++ geometry primitives	5		20%			100%					1			5				6
DMTF-16570-20	DM-201	reorg	Qserv: unit testing (controller module)	5		100%	10%	10%					5	1	1					6	design, toy prototype
DMTF-16570-21	DM-202	reorg	Qserv: unit testing (query execution)	5		100%	10%	10%					5	1	1					6	design, toy prototype
	DM-217	reorg	Qserv design: data partitioning	5		10%		100%					1		5					6	Experimenting with no-subchunking based approach
	DM-219	reorg	Qserv worker scheduler – code cleanup	5		100%					5					5
	DM-222	reorg	Reference Test Server using new XRootD	4					100%					4			4
DMTF-16570-24	DM-203	testing	Qserv: setup new cluster at IN2P3 for continuous integration/testing	4					100%					4	4
	DM-58	config	Packaging: zookeeer and kazoo	4					100%					4	4
	DM-223		S14 database schema and tune up	2	100%			50%					2			1					3
DMTF-16570-28	DM-204		MySQL wrappers	2	100%			50%					2			1					3
			Improvements to Qserv build system	2		10%					100%			0					2		2
	DM-224	reorg	Switching to MariaDB	2					100%					2	2
DMTF-16570-19			Qserv: setup infrastructure for continuous integration					0
DMTF-16570-22			Qserv: unit testing (admin/loading)	5					0
				0
			All-hands LSST meeting	5	100%	100%	100%	100%			100%		5	5	5	5			5		25
			hiring	10	100%	20%	20%	10%		10%	10%		10	2	2	1		1	1		17
			group mgmt	120	20%					24					24	includes things like reports, planning, statement of works, budget, cost estimates, responding to ad hoc requests from upper mgmt, etc
				0
			XLDB					0
			XLDB-Brazil workshop	10	100%		50%					10		5					15	early June. 2 day mtg + travel and prep
			XLDB-healthcare workshop	8	100%		50%					8		4					12	Spring 2014. 2 day mtg + travel. Incl preparing
			XLDB long term future, strategic partnerships	10	100%					10					10

				assigned [days]:		105	83	24	52	54	26	39	59	417
				FTE %:		100%	100%		50%	50%	30%	46%	50%
				Fte [days]:		120	120		60	60	36	55	60	511
				diff [days]:		15	37		8	6	10	16	1	94
				% loaded:		88%	69%		87%	90%	71%	71%	98%	82%

				Duration 6 months (March-Aug), assuming 20 days / month					120

## W2014
#	Activity Name	Part of	Duration		assignee					days per assignee					total	Predecessors	Notes/description	completed as of 2/1/2014
			description	[days]	Jacek	Daniel	K-T	Doug	Serge	Bill	Andy	in2p3	Jacek	Daniel	K-T	Doug	Serge	Bill	Andy	in2p3	days			%	days
1	Qserv block-level design	Qserv redesign	4 weeks	20	20%	25%	10%	10%	10%	10%	10%	10%	4	5	2	2	2	2	2	2	21			100%	21
2	Qserv: mapping existing code to new block design	Qserv redesign	3 days	3	5%	50%				50%			0	2				2			3	1		100%	3
3	Qserv: User-friendly communication (syntax support)	Qserv redesign	4 weeks	20	10%	30%	5%	0%	0%				2	6	1					9	1	Support correctly all syntax, eg, detect/reject unsupported syntax etc	0%	0
4	Qserv: User-friendly communication (message passing beyond SQL)	Qserv redesign	0	0	30%	30%	5%	5%	10%					0	1, 3			0
5	Qserv: hackathon I (fall 2013)	Qserv redesign	1 week	5	100%	100%	30%	100%	100%	100%	50%	100%	5	5	2	5	5	5	3	5	34			100%	34
6	Qserv: supporting match tables	Qserv redesign	2 weeks	10	0.1%	5%			70%				0	1			7				8			0%	0
7	New XRootD RPC interface implementation	Qserv redesign	6 weeks	30	0.1%	10%					30%		0	3					9		12			100%	12
8	Plug in new xrootd client (DMTF-1650-075)	Qserv redesign	4 weeks	20	0.1%	50%			10%		20%		0	10			2		4		16	5		0%	0
9	Qserv design: distributed metadata / state	Qserv redesign	1 month	20	50%	5%	5%		5%				10	1	1		1				13			80%	10
10	Qserv: code reorg	Qserv redesign	1 week	5	40%	40%	25%		5%			40%	2	2	1		0			2	8	2		100%	8
11	Qserv: query representation (subset of DMTF-1650-150)	Qserv redesign	1 month	20	0.1%	50%			5%				0	10			1				11			0%	0
12	Qserv: code cleanup and making framework stable	Qserv redesign	1 month	20	5%	50%			5%	20%			1	10			1	4			16	1,2,3,7,9,10,11,12,14,16,17,23,25		70%	11
13	Qserv design: data ingest and loading	Data ingest and loading	4 weeks	20	50%		5%	20%	10%		15%	5%	10		1	4	2		3	1	21			80%	17
14	Data export from pipeline – code refurbishing	Data ingest and loading	4 weeks	20	1%		10%		20%				0		2		4				6			0%	0
15	Qserv: Logging (software API)	Logging framework redesign	2 weeks	10	10%	30%	15%		0%	50%	5%	10%	1	3	2			5	1	1	12		come up with, and implement logging framework	20%	2
16	Qserv: Logging (distributed log collection)	Logging framework redesign	2 weeks	10	10%	30%	15%		0%	50%	5%		1	3	2			5	1		11	16	come up with, and implement logging framework	0%	0
17	Qserv: automated testbed	auto testing	4 weeks	20	5%	5%	5%					50%	1	1	1					10	13		high priority, schedule first	30%	4
18	Qserv: setup infrastructure for continuous integration	continuous integration	4 weeks	20	10%	15%	5%	0%		25%		30%	2	3	1			5		6	17			60%	10
19	Qserv: unit testing (controller module)	continuous integration	2 weeks	10	1%	40%				25%			0	4				3			7				0
20	Qserv: unit testing (query execution)	continuous integration	2 weeks	10	1%	40%				25%			0	4				3			7				0
21	Qserv: unit test spec (admin/loading)	continuous integration	2 weeks	10	30%					0%	3					3			50%	2
22	Qserv: build system	continuous integration	3 weeks	15	5%	40%	5%		5%			10%	1	6	1		1			2	10	5		100%	10
23	Qserv: setup new cluster at IN2P3 for continuous integration/testing	continuous integration	2 weeks	10	0%	0%					0%					0		schedule for February		0
24	Qserv: packaging	Distribution server redesign	2 months	40	5%	5%	3%		3%			50%	2	2	1		1			20	26	5		80%	21
25	Qserv documentation	docs	90 days	90	3%	3%	3%		3%	3%	2%	5%	3	3	3		3	3	2	5	20		ongoing	80%	16
26	W14 database tune up (replaces DMTF-1650-120)	Database tuneup	2 weeks	10	10%					1					1		includes merge engine	50%	1
27	MySQL wrappers		3 weeks	15	60%					9					9			100%	9
28	Association Pipeline		2 weeks	10					100%					10				10
29	Xldb-2013 report writing		4 weeks	20	10%	20%	3%					2	4	1					7
30	FDR prep		1 month	20	25%		25%					5		5					10
31	FDR		1 week	5	100%		100%					5		5					10
32	group mgmt		4.5 months	90	20%					18					18		includes things like reports, planning, paperwork, etc

				assigned [days]:		88	87	30	11	40	35	23	53	367				60.88%
				FTE %:		100%	100%	100%	13%	50%	50%	30%
				Fte [days]:		90	90	90	11	45	45	27		398
				diff [days]:		2	3	60	0	5	10	4		84
				% loaded:		98%	96%	33%	98%	89%	78%	86%		92%

				Duration Oct 1st – Feb 28 (5m-xmas)=4.5months, 20 days / month					90
				75%, 2 months